## Clear-Out
University of Pennsylvania
Perelman School of Medicine
Lab Clear-Out Plan
Activity | Detail | Action by: | Faculty/Staff Assignment (or N/A) | Deadline
Planning | Create clear-out plan (using this matrix) | Lab
Dispose of unwanted chemicals and chemical contaminated sharps | Empty all chemical fume hoods, drawers, storage cabinets, closets, cold rooms, flammable liquids cabinets, biosafety cabinets, refrigerators and freezers of all chemicals. Check shared facilities for materials that belong to your lab. | Lab
| Label all chemical containers with the proper chemical name. Close all containers securely. | Lab
| Determine which chemicals are usable. Transfer responsibility for these chemicals to a party willing to accept it. If a new user cannot be found, dispose of materials following Penn's Laboratory Waste Guidelines. | Lab
| Contact EHRS for waste collection. Do not pour chemicals down drains or discard them in the trash. | Lab, EHRS
| Remove gas connections, replace cylinder caps, and return cylinders to suppliers. If cylinders are non-returnable, please contact EHRS. | Lab, EHRS
| Chemical contaminated sharps: Segregate from other sharps into sharps containers and label "Chemical contaminated Sharps Waste-Do Not Autoclave" Dispose of either by placing it in a Stericycle infectious waste box or in Curtis Bay reusuable sharps container. | Lab
Dispose of unwanted biological materials | Identify an appropriate person to take responsibility for retained samples. | Lab
| Empty cold rooms, biosafety cabinets, refrigerators and freezers of all biological materials. Check shared facilities for materials that belong to your lab. | Lab
| Dispose of infectious waste sharps either by: placing it in an Curtis Bay reusable sharps container or autoclave sharps container and dispose through PSOM’s infectious waste stream. | Lab
| Dispose of unwanted animal and human tissue. Do not separate specimens from liquid preservative (formalin/ IPA/EtOH, etc.) Contact EHRS for waste collection. | Lab/EHRS
| If human tissue is recognizable contact Dwayne Hallman, Department of Cell and Developmental Biology, 215-898-8054, to arrange for its disposal. Place other human tissue specimens in a biohazard waste bag, autoclave and dispose through PSOM's infectious waste stream. | Lab
| Discard animal tissue by placing it in a biohazard waste bag, autoclave and dispose through PSOM's infectious waste stream. Recognizable animal parts or carcasses must be disposed in a ULAR vivarium morgue. | Lab
| If appropriate tissue disposal is uncertain, contact an EHRS Biosafety Officer 215-898-4453 | Lab, EHRS
| If tissue was stored in a refrigerator or freezer - defrost, clean and disinfect the refrigerator and freezer when emptied. | Lab
| Empty or new infectious waste items (red bags, infectious waste boxes, sharps container, boxes of new syringes) must be either transferred to a lab willing to accept these items or disposed of as infectious waste. | Lab
Clean and decontaminate all surfaces | Clean and decontaminate all surfaces where hazardous materials have been used. 1. Use an appropriate cleanser to remove chemical contaminants. 2. Use an appropriate EPA approved disinfectant for biological contamination. If unsure about what to use contact EHRS. | Lab
Dispose of unwanted laboratory equipment. | Update asset management documentation to reflect disposal of scientific equipment | Div/Dept
| Determine whether equipment can be reallocated or recycled | Lab
| Decontaminate scientific equipment | Lab
| Deface or cover hazard labels on equipment to be moved or discarded. | Lab
| If moving biological safety cabinets, decontaminate before moving and recertify before use in the new location. Contact Micro-Clean or TSS to set up an appointment. | Lab
| When discarding laboratory equipment: remove capacitors, transformers, mercury switches, mercury thermometers, radioactive sources, chemicals and biohazards before disposal. Contact EHRS for disposal of hazardous materials. | Lab, EHRS
| Ensure proper Battery Disposal. Standard alkaline batteries can be placed in regular trash. Contact EHRS for disposal of all other batteries. | Lab, EHRS
| Contact SPO for assistance with movement of safed equipment, as well as coordination with a disposal or repurposing vendor | Lab
Dispose of unwanted computing and electronic equipment. | Contact PMACS http://www.med.upenn.edu/pmacs/recycling.html prior to donating, recycling or disposing of any equipment. | Lab, PMACS
| The PSOM Computer Recycling Program is coordinated by PMACS in conjunction with Elemental, Inc. (www.eleminc.com). | Lab, PMACS
Dispose of unwanted furniture. | Contact Space Planning and Operations to facilitate responsible disposal, recycling, donation or reuse (dcaval@pennmedicine.upenn.edu). | Lab
Dispose of unwanted records and documents. |  | Lab
Archive records to be stored off site. |  | Lab
Controlled substances | Controlled substances are regulated by the United States Drug Enforcement Administration (DEA). Detailed information relating to controlled substances can be found online at www.deadiversion.usdoj.gov Controlled drugs must be secured and properly disposed by the licensed registrant. | Lab
Radioactive materials | Amend your radioactive material license to add the new space and delete the old. Doing so, will initiate contact with the Radiation Safety group so we can assist you with moving out of your space. Please refer to the Radiation Safety User Guide for a summary of requirements. | Lab, EHRS
Clean and disinfect lab bench tops. |  | Lab
Clean and disinfect equipment to remain in lab. |  | Lab
Remove debris. |  | Lab
Carefully inspect lab area |  | Lab
Complete Lab Clearance Form on EHRS website. |  | Lab
EHRS conducts lab sweep |  | EHRS
SPO walk through, review |  | SoM
Housekeeping cleans lab. |  | SoM
Facilities work requests (repairs to any furniture, patch & paint, floor tile replacement) |  | Lab, Div/Dept, SoM
Ensure keys to desk and lab bench drawers are left behind, or if lost, request replacement |  | Lab, Dept, SoM
Return handset phones to ISC or reallocate within Dept |  | Lab, Div/Dept, SoM, Phone LSP
Request deactivation of/change funding source for any active dataports |  | Lab, Div/Dept, SoM

## Move
University of Pennsylvania
Perelman School of Medicine
Lab Move Plan
Activity | Detail | Action by: | Faculty/Staff Assignment (or N/A) | Deadline
Planning | Create clear-out plan (using this matrix) | Lab
Chemicals: Prepare to move chemicals or dispose of unwanted chemicals and chemical contaminated sharps. | Empty all chemical fume hoods, drawers, storage cabinets, closets, cold rooms, flammable liquids cabinets, biosafety cabinets, refrigerators and freezers of all chemicals. Check shared facilities for materials that belong to your lab. | Lab
| Label all chemical containers with the proper chemical name. Close all containers securely. | Lab
| Determine which chemicals you wish to keep and move to your new lab. Transfer responsibility for unwanted chemicals to a party willing to accept it. If a new user cannot be found, dispose of materials following Penn's Laboratory Waste Guidelines. | Lab
| Contact EHRS for waste collection. Do not pour chemicals down drains or discard them in the trash. | Lab, EHRS
| Remove gas connections, replace cylinder caps, and return cylinders to suppliers. If cylinders are non-returnable, please contact EHRS. | Lab, EHRS
| Chemical contaminated sharps: Segregate from other sharps into sharps containers and label "Chemical contaminated Sharps Waste-Do Not Autoclave" Dispose of either by placing it: in Stericycle infectious waste box or in Curtis Bay reusuable sharps container. | Lab
Biological Materials: Prepare to move or dispose of unwanted biological materials. | Check cold rooms, biosafety cabinets, refrigerators and freezers for all biological materials. Determine what needs to be moved. Label refrigerators and freezers to be moved. Check shared facilities for materials that belong to your lab. | Lab
| Dispose of infectious waste sharps either by: placing it in an Curtis Bay reusable sharps container or autoclave sharps container and dispose through PSOM’s infectious waste stream. | Lab
| Dispose of unwanted animal and human tissue. Do not separate specimens from liquid preservative (formalin/ IPA/EtOH, etc.) Contact EHRS for waste collection. | Lab/EHRS
| If human tissue is recognizable contact Dwayne Hallman, Department of Cell and Developmental Biology, 215-898-8054, to arrange for its disposal. Place other human tissue specimens in a biohazard waste bag, autoclave and dispose through PSOM's infectious waste stream. | Lab
| Discard unwanted animal tissue by placing it in a biohazard waste bag, autoclave and dispose through PSOM's infectious waste stream. Recognizable animal parts or carcasses must be disposed in a ULAR vivarium morgue. | Lab
| If appropriate tissue disposal is uncertain, contact an EHRS Biosafety Officer 215-898-4453 | Lab, EHRS
| For refrigerators and freezers to remain - defrost, clean and disinfect the refrigerator and freezer when emptied. | Lab
| Take empty or new infectious waste items (red bags, infectious waste boxes, sharps container, boxes of new syringes) to you new lab. If unwanted, these items must be either transferred to a lab willing to accept these items or disposed of as infectious waste. | Lab
| If moving samples on LN2, ensure your LN2 supply is available in new space | Lab
Radioactive materials | Amend your radioactive material license to add the new space and delete the old. Doing so, will initiate contact with the Radiation Safety group to assist you with moving out of your space. Please refer to the Radiation Safety User Guide for a summary of requirements. | Lab
Controlled substances | Controlled substances are regulated by the United States Drug Enforcement Administration (DEA). Detailed information relating to controlled substances can be found online at www.deadiversion.usdoj.gov. | Lab
Dispose of unwanted laboratory equipment. | Update asset management documentation to reflect disposal of scientific equipment | Lab
| Determine whether equipment can be reallocated or recycled | Lab
| Decontaminate scientific equipment | Lab
| Deface or cover hazard labels on equipment to be moved or discarded. | Lab
| If moving biological safety cabinets, decontaminate before moving and recertify before use in the new location. Contact vendor to set up an appointment. | Lab
| When discarding laboratory equipment: remove capacitors, transformers, mercury switches, mercury thermometers, radioactive sources, chemicals and biohazards before disposal. Contact EHRS for disposal of hazardous materials. | Lab, EHRS
| Ensure proper Battery Disposal. Standard alkaline batteries can be placed in regular trash. Contact EHRS for disposal of all other batteries. | Lab, EHRS
| Contact SPO for assistance with movement of safed equipment, as well as coordination with a disposal or repurposing vendor | Lab
Dispose of unwanted computing and electronic equipment. | Contact PMACS http://www.med.upenn.edu/pmacs/recycling.html prior to donating, recycling or disposing of any equipment. | Lab, PMACS
| The PSOM Computer Recycling Program is coordinated by PMACS in conjunction with Elemental, Inc. (www.eleminc.com). | Lab, PMACS
Dispose of unwanted furniture. | Contact Space Planning and Operations to facilitate responsible disposal, recycling, donation or reuse (dcaval@pennmedicine.upenn.edu). | Lab
Dispose of unwanted records and documents. |  | Lab
Archive records to be stored off site. |  | Lab
Order new equipment for delivery to new lab location. |  | Lab
Update building listserve subscription for new lab location. |  | Lab
Notify ISC of new locations for V/D ports and phone numbers. |  | Lab
Inform vendors of change of address. |  | Lab,Div/Dept
Notify SoM Mail Room of location change. |  | Lab,Div/Dept
Ensure BEN Buy's shipping address is updated |  | Lab, Div/Dept/BA
Contact vendors of equipment under service contract and or warrantee to determine their participation in equipment relocation. |  | Lab,Div/Dept
Schedule vendors to pack equipment for shipping (imaging systems, floor mounted centrifuges, etc.) |  | Lab,Div/Dept
Schedule transfer of voice/data service. |  | Lab,Div/Dept
Reduce cell lines if possible. |  | Lab,Div/Dept
Moving Contractor delivers moving materials. |  | Lab,Div/Dept
Identify temporary cell storage. |  | Lab
Label floor mounted equipment w/ mover's labels and architect's equip. number. |  | Lab
Pack personal effects and under bench cabinets and drawers. |  | Lab
Vendors secure equipment for relocation. |  | Lab
Contact vendor to decontaminate BSCs. |  | Lab
Vendor to deliver new compressed gas to new lab location. |  | Lab,Div/Dept
FRES turns over keys. |  | FRES
Request FRES disconnect any hard-piped vacuum lines from BSCs |  | Lab, FRES
Remove cell lines from incubators. |  | Lab
Drain water jacketed incubators, if applicable |  | Lab
Stuff freezers with bubble wrap. |  | Lab
Chemical mover packs and moves reagents, chemicals, hazardous materials and contents of cold rooms and refrigerators. |  | Lab
Mover relocates floor mounted equipment. |  | Lab
Mover packs lab benches, shelves, tables, glassware - all but contents of undercounter cabinets and drawers. |  | Lab
Mover relocates remaining contents of lab. |  | Lab
Vendor or mover installs BSC; lab personnel set up as needed. |  | Lab
Vendor to certify BSC. |  | Lab
Unpack undercounter and personal effects. |  | Lab
Reconnect incubators, bring up to temperature, reconnect to gas. |  | Lab
Relocate cell lines and resume incubator operations. |  | Lab
Work recommence in BSC. |  | Lab
Vendor recalibrates equipment (imaging systems, centrifuges). |  | Lab
Clean fume hood interior at vacated lab. |  | Lab
Clean and disinfect lab bench tops at vacated lab. |  | Lab
Clean and disinfect equipment to remain In vacated lab. |  | Lab
Dispose of sharps in vacated lab. |  | Lab
Remove debris from vacated lab. |  | Lab
Sweep of vacated lab by EHRS. |  | EHRS
Housekeeping cleans vacated lab. |  | SoM
Facilities work requests (repairs to any furniture, patch & paint, floor tile replacement) |  | Lab, Div/Dept, SoM
Ensure keys to desk and lab bench drawers are left behind, or if lost, request replacement |  | Lab, Dept, SoM
Return handset phones to ISC or reallocate within Dept |  | Lab, Div/Dept, SoM, Phone LSP
Request deactivation of/change funding source for any active dataports |  | Lab, Div/Dept, SoM