## Risk Prioritization Worksheet
| Risk | [9 empty] | ` |  |  |  |  | Mitigation Status
| Risk Description | 42 | [8 empty] | Proposed Mitigation Action | Adjusted Risk |  | 18 | 24 | Log History of Mitigation Action Implementation Status
ref | Risk Description /Threat and Potential Loss (include date risk identified) | Probability of Loss | Consequence | Risk Score | #REF! | #REF! | #REF! | #REF! | Risk Value | #REF! | Proposed Mitigation Action | Loss Probability | Loss Consequence | Revised Score | Risk Value Reduction
1 | ePHI located on DeskTop in Faculty Member X's office is not routinely backed up. Risk = Loss of PHI (Identified in Gap Analysis) | 4 | 4 | 16 | #REF! | #REF! | #REF! | #REF! | High | #REF! | Staff assigned to complete daily back-ups on CD, storing most current off-site | 1 | 4 | 4 | 12 | Target date for completion 04/25/05 - on track 09/01/04
2 | Software vendor ___________'s employees use dial-in or Internet access to monitor systems’ performance—potential for disgruntled employee to gain access. Vendor uses common login (ID and passwords). Potential Loss, unauthorized disclosure and loss of data integrity (identified in Gap Analysis) | 2 | 5 | 10 | #REF! | #REF! | #REF! | #REF! | Medium | #REF! | Deactivate all vendor accounts, activate only with prior coordination and ‘need’ | 1 | 2 | 2 | 8
3 | Undocumented databases containing PHI stored on local hard drives. Potential Loss = unauthorized disclosure or loss of PHI (Risk exists, but not identified in Gap Analysis) | 4 | 4 | 16 | #REF! | #REF! | #REF! | #REF! | High | #REF! | Employ automated asset inventory system to track files and devices | 3 | 4 | 12 | 4
4 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
5 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
6 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
7 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
8 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
9 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
10 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
11 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
12 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
13 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
14 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
15 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
16 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
17 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
18 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
19 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
20 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
21 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
22 |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | Low | #REF! |  |  |  | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0
|  |  |  | 0 | [9 empty] | 0 | 0